# Project Scope Intake Form

This form gathers the essential details about a project to ensure clear objectives, expectations, and resource alignment.

- CSM is responsible for completing Sections 1-3 and submitting it to the SDM via the Virtual Assistant.

- If additional details are needed, a follow-up meeting will be scheduled.

1: General Information

- Project Name: IPELRA Conference App Development

- Client: IPELRA

- Requester Contact Information:

  - Name: Angie Miller

  - Email: Click or tap here to enter text.

  - Phone: Click or tap here to enter text.

- Date of Submission: 4/1/2026

- Desired Project Start Date: 4/1/2026

- Target Completion Date: 5/31/2026

# 2: Objectives & Success Criteria

- What is the primary goal of this project? (Check all that apply)

☐ Process improvement

☐ Data analysis/reporting

☐ System implementation

☐ Compliance requirement

☒ Other (please specify): App Development

- Describe the problem or opportunity this project is addressing:

MGP has been asked to build an app to support the IPELRA Conference.

- What are the key success criteria for this project? (e.g., specific deliverables, efficiency improvements, compliance adherence)

Core Functions

- Mobile-friendly web link vs full app download needed

- List of sponsor stops that attendees can complete

- Each stop is unlocked by either:

  - Scanning a QR code at the sponsor table

OR

  - Completing a simple one-question prompt

- App tracks attendee progress/points as they complete stops

- When finished, attendee sees a “Completed Passport” confirmation for prize entry

- Easy for IPELRA to add/update sponsors, logos, and prompts/tagline

• Each sponsor gets a unique QR code
• Display sponsor name, logo, and brief tagline in the app
• Option to include a short prompt (optional)
• Basic usage metrics (ex: number of scans/check-ins)

Light Gamification

• Points for each completed sponsor stop
• Simple progress bar or checklist
• Optional “bonus stops” for higher-tier sponsors

# 3: Scope & Deliverables

- What specific deliverables are expected from this project? (Check all that apply)

☐ Report/Analysis

☐ Dashboard/Visualization

☐ Software Implementation

☐ Training/Documentation

☒ Other: App Development

- What systems, tools, or datasets will be involved?

Click or tap here to enter text.

- Internal databases (please specify):

Click or tap here to enter text.

- External vendor platforms (please specify):

Click or tap here to enter text.

- Manual processes requiring automation:

Click or tap here to enter text.

- Other:

Click or tap here to enter text.

- Are there any constraints or limitations? (e.g., data access, resource availability, legal restrictions)

Click or tap here to enter text.

# 4: Resource Allocation & Dependencies

- Estimated analyst hours needed: Click or tap here to enter text.

- Will this project require coordination with external vendors or teams?

☐ Yes (please specify): Click or tap here to enter text.

☐ No

- Are there existing projects that may impact this initiative?

☐ Yes (please specify): Click or tap here to enter text.

☐ No

# 5: Risk & Approval

- Potential risks associated with this project:

☐ Data security concerns

☐ Compliance/legal risks

☐ Resource limitations

☐ Unclear requirements

☐ Other: Click or tap here to enter text.

# 6: User Stories

IPELRA needs a simple, mobile-friendly “conference passport” experience because attendees currently lack an easy way to complete sponsor stops and confirm prize eligibility. We will deliver a web-accessible passport that lets attendees unlock sponsor stops (via QR scan or a quick prompt), tracks progress/points, and confirms completion—while enabling IPELRA to maintain sponsor content and view basic participation metrics.

- Attendee – Sponsor Stops
 As an attendee, I want to see a list of sponsor stops I can complete, so that I can participate in the conference passport activity.

- Attendee – Unlock Stop (QR or Prompt)
 As an attendee, I want to unlock a sponsor stop by either scanning a QR code at the sponsor table or completing a one-question prompt, so that I can complete stops even if one method isn’t available.

- Attendee – Progress & Points
 As an attendee, I want the passport to track my completed stops and points with a simple progress indicator, so that I know how close I am to finishing.

- Attendee – Completion Confirmation
 As an attendee, I want to receive a “Completed Passport” confirmation when I finish the required stops, so that I can confirm I’m eligible for prize entry.

- IPELRA Admin – Manage Sponsors & Content
 As an IPELRA admin, I want to add/update sponsors (name, logo, tagline, optional prompt/bonus designation) and generate a unique QR code per sponsor, so that the passport stays current and easy to maintain.

- IPELRA Admin – Basic Metrics
 As an IPELRA admin, I want to view basic usage metrics (e.g., number of scans/check-ins per sponsor), so that I can understand participation and sponsor engagement.

# 7: Requirements

### FUNCTIONAL REQUIREMENTS

- FR 01: The solution must be accessible via a mobile-friendly web link (no full app download required).

- FR 02: The solution must display a list of sponsor stops available for attendees to complete.

- FR 03: Each sponsor stop must be completable by either (a) QR code scan at the sponsor table or (b) completing a single-question prompt.

- FR 04: The solution must track attendee completion status per sponsor stop and maintain a points total based on completed stops.

- FR 05: The attendee experience must include a simple progress indicator (e.g., progress bar and/or checklist).

- FR 06: Upon completing the defined requirements, the solution must display a “Completed Passport” confirmation for prize entry verification.

- FR 07: Admin users must be able to add/update sponsors including sponsor name, logo, brief tagline, and optional prompt.

- FR 08: The solution must generate and associate a unique QR code per sponsor for use at sponsor tables.

- FR 09: The solution must support optional bonus stops for higher-tier sponsors (i.e., a designated set of bonus stops that can award additional points and/or count separately).

- FR 10: The solution must provide basic usage metrics such as number of scans/check-ins per sponsor stop.

- FR 11: Branding reflects IPELRA conference branding standards.

### TECHNICAL REQUIREMENTS

- TR 01: The attendee experience must function on mobile devices via a web link and be responsive for common mobile screen sizes.

- TR 02: The solution must support QR code scanning from a mobile device (camera-enabled scanning within the experience or an equivalent scanning workflow).

- TR 03: Sponsor data (name/logo/tagline/prompt/bonus designation) must be stored in a maintainable data source that supports admin updates without redevelopment.

- TR 04: Attendee progress and points must be stored in a way that supports: completed-stop validation, completion confirmation, and metrics reporting.

- TR 05: Admin access must be restricted to authorized IPELRA users for sponsor/content updates and metrics viewing.

- TR 06: The solution must produce/export sponsor QR codes in a format suitable for printing/display at tables.

## 8: Acceptance Criteria

- AC 01: GIVEN an attendee opens the passport link on a phone WHEN the page loads THEN the interface displays correctly in a mobile-friendly layout and provides access to sponsor stops.

- AC 02: GIVEN sponsor stops exist WHEN an attendee views the stops list THEN each stop displays the sponsor name, logo, and tagline (where provided).

- AC 03: GIVEN an attendee selects a sponsor stop WHEN they choose the QR option and scan the sponsor’s QR code THEN the stop is marked completed and points are added per the configured rules.

- AC 04: GIVEN an attendee selects a sponsor stop WHEN they choose the prompt option and submit a response to the single-question prompt THEN the stop is marked completed and points are added per the configured rules.

- AC 05: GIVEN an attendee completes one or more stops WHEN they return to the main passport view THEN the progress indicator reflects the current completion count/status and current points total.

- AC 06: GIVEN an attendee has completed the defined completion threshold WHEN they view the passport status THEN the solution displays a “Completed Passport” confirmation.

- AC 07: GIVEN an authorized admin is logged in WHEN they add or update a sponsor’s name/logo/tagline/prompt/bonus designation THEN the attendee view reflects the changes without code changes.

- AC 08: GIVEN an admin creates or updates a sponsor WHEN they request the sponsor QR code THEN a unique QR code is generated and can be exported for printing/display.

- AC 09: GIVEN sponsors are configured (including any bonus stops) WHEN an attendee completes a bonus-designated stop THEN points/progress reflect the bonus stop configuration.

- AC 10: GIVEN attendee activity has occurred WHEN an admin views metrics THEN the solution shows basic counts such as number of scans/check-ins per sponsor stop.

- AC 11: GIVEN up to 500 users are using the solution simultaneously, THEN solution functionality is unaffected.

# 9: Recommended Solution Approach

Recommended Platform: M365 / Power Platform solution (web-based)
 This request is primarily a conference workflow and engagement experience (passport completion, content management, and basic reporting) rather than a spatial/GIS problem. Discovery emphasizes a mobile-friendly web link, sponsor content maintenance (logos/taglines/prompts), QR-based check-ins, and simple metrics—well aligned to a lightweight M365/Power Platform web experience with an admin-maintainable sponsor dataset and stored completion/points records.

# 10: Project Milestones (SDM → CSM → Delivery aligned)

### Milestone 1 — Scope & Success Criteria Confirmation (SDM/CSM)

- Objective: Lock a defensible scope aligned to conference needs and confirm “done” criteria.

- Key Inputs: Discovery request (core functions, gamification items, dates), sponsor stop concepts, completion expectations.

- Key Outputs: Approved scope summary, confirmed completion rules (required stops/points), confirmed admin responsibilities.

### Milestone 2 — Content Model & Experience Design (Delivery)

- Objective: Define the sponsor data model and attendee/admin experience flows.

- Key Inputs: Sponsor fields (name/logo/tagline/prompt/bonus), QR requirement, metrics examples.

- Key Outputs: Sponsor data structure, attendee flow (list → unlock → progress → completion), admin flow (manage sponsors → generate QR → view metrics).

### Milestone 3 — Build & Configure Passport Experience (Delivery)

- Objective: Implement the attendee passport, admin maintenance capability, QR generation, and progress/points tracking.

- Key Inputs: Approved designs and data model, point/progress rules, sponsor content assets (initial set).

- Key Outputs: Working web-accessible passport experience; admin management interface; QR codes generated per sponsor.

### Milestone 4 — Validation, Content Load, & Launch Readiness (CSM/Delivery)

- Objective: Ensure the solution works end-to-end for the conference and IPELRA can operate it.

- Key Inputs: Final sponsor list/logos/taglines/prompts, device/browser testing expectations, completion verification approach.

- Key Outputs: UAT sign-off, sponsors loaded, QR codes packaged for distribution, launch-ready solution with basic metrics available.

# 11: Notable Gaps & Assumptions

### Gaps (not provided in discovery)

- Systems/tools/datasets involved were not specified (blank in intake), including where sponsor and attendee progress data should live.

- Attendee identification method is not defined (anonymous vs tied to registration/email), which impacts progress tracking, duplicate prevention, and prize verification.

- Completion rule definition is not explicit (e.g., “all stops” vs “N stops” threshold; whether bonus stops are required or optional).

- Points model is not explicitly defined (points per stop, bonus weighting).

- Metrics detail is only described at a high level (“basic usage metrics” example given) and needs confirmation on exact reporting view/format.

### Assumptions (required to scope delivery now)

- The solution will be a web-accessible, mobile-friendly experience (per discovery) rather than a native app store deployment.

- Sponsor stops will be maintained by IPELRA through a simple admin interface that supports add/update of sponsor name/logo/tagline and optional prompt.

- “Basic metrics” will at minimum include count of check-ins/scans per sponsor stop as described in discovery.

- QR codes are unique per sponsor and will be printed/displayed by sponsors at their tables.

- No external integrations are required.

- App needs to support up 500 concurrent users.

- Solution will be hosted in MGP’s environment.

### Questions

Should attendee participation be tracked anonymously (device/session-based) or tied to a known identifier (e.g., registration email/ID)?

What information will they want back in terms of users, usage, activity, etc.

Number of anticipated users.