CONFIDENTIAL — IPELRA INTERNAL

Conference Passport App

IPELRA Staff Checklist

IPELRA Annual Conference 2026  ·  Eagle Ridge Resort, Galena, IL

How to use this checklist: These are the things only IPELRA can provide or decide. A separate sheet goes to sponsors. Once all items below are checked off and sponsor info is collected, we handle the rest — no technical work required from your end.

KEY MILESTONES

| Target | Target | Go-Live | Lock |
| --- | --- | --- | --- |
| Late Aug 2026 All sponsor info collected & staff checklist complete | Early Sept 2026 App configured & in final testing | Oct 5, 2026 Passport app opens for attendees | Oct 7, 2026 Passport closes — prize drawing |

1 · BRANDING & LOGOS

☐  Official IPELRA logo file  [REQUIRED]

PNG or SVG file, transparent background preferred. Used in the app and in every email sent to attendees. A transparent background ensures it looks correct on all screen colors. A screenshot from the website may work but can appear blurry on high-resolution phone screens — the actual file from your designer is best.

2 · PEOPLE & ACCESS

☐  Admin email addresses  [REQUIRED]

The email address(es) for each person who needs access to the admin portal (dashboard, attendee list, export, etc.). These people receive a login link by email — no password needed. Typically 2–4 people.

3 · SPONSOR INFORMATION

☐  Final sponsor list with tiers  [REQUIRED]

A complete list of all participating exhibitors and whether each is Gold or Platinum tier. This determines point values (Gold = 100 pts, Platinum = 150 pts).

☐  Completed sponsor info sheets returned  [REQUIRED]

Each sponsor fills out their info sheet and returns it to you. Forward everything to us at once. See the companion document: Sponsor Information Sheet.

4 · CONFERENCE DETAILS TO CONFIRM

☐  Prize station location at Eagle Ridge  [CONFIRM]

The app currently directs completers to "the Prize Station near the conference registration desk." Please confirm this is accurate — if the prize station will be somewhere else, let us know before launch.

☐  Passport open/close dates and times  [CONFIRM]

Currently set to open October 5, 2026 and lock October 7, 2026. If either date or time needs to change, let us know.

☐  Prize & drawing process  [CONFIRM]

The app tracks every attendee who completes the passport. We can export a CSV of completers for a prize drawing. Confirm what the prize is and how you plan to run the drawing so the app wording matches.

☐  Review the Help & FAQ page  [CONFIRM]

The app has a built-in help section that answers common attendee questions. We'll share the draft text — please read through it and flag anything that doesn't match how you plan to run the event.

5 · DURING THE CONFERENCE — STAFF DUTIES

☐  Print QR codes for each sponsor booth

We will generate a QR code card for each sponsor. Print one per booth and place it on the table. Sponsors don't need to do anything technical — attendees scan to open that sponsor's page in the app.

☐  Activate the passport in the admin portal on opening day

The passport starts in "off" mode. On the morning of October 5, log into the admin portal and flip the passport to Live.

☐  Monitor the admin dashboard during the conference

The dashboard shows real-time check-ins, completions, and flagged activity. Typically no action needed — just a good way to see how engagement is going.

☐  Help attendees who didn't receive their login email

Direct them to the login page to request a new link. Links expire in 15 minutes — if they waited too long, they just request another one. No password, no account to reset.

6 · AFTER THE CONFERENCE

☐  Export completed attendees list for prize drawing

In the admin portal, use the Export page to download a CSV of all attendees who completed the passport.

☐  Run Conference Reset to archive data  [OPTIONAL]

The admin portal includes a Reset function that archives all attendee and check-in data from this year. Not urgent — do it when you're ready to clean up for next year.

IPELRA Annual Conference 2026  ·  Eagle Ridge Resort, Galena, IL  ·  Confidential — Staff Use Only